## Sheet1
Task | Status
Gather data | Completed
Load data using Python | Completed
Refine data into usable format | Completed
Convert data into csv | Completed
Data is ready | Completed
Perform exploratory analysis: -Query time vs No.of players -Guild vs no.of players -Query time vs Guild -Create custom wow map and plot no.of playes based on wow zones (tricky part) -Provide insights from the above analysis | InProgress
Featurization: -Apply PCA on the dataset and come up with new features for unsupervised learning -Check if SVM can be applied on this data | Yet to start
Create interim report and submit by Jan 5th | InProgress
Unsupervised learning: -Create clusters (K-Means) and group players -Come up with insights on which kind of players fall into which groups | Yet to start
Recommendations: -Apply NMF and KNN on Avatar id vs Guild with (played/not played as data values) and recommend new guilds to users | Yet to start
Timeseries forecasting for Player visits | Yet to start
Churn: -Can we find out if a player would churn if he is playing in a particular guild/level/class/pattern? | Yet to start
Prepare data input in a way it can be used for neural networks | InProgress
Apply neural networks to find the patterns (this is a tricky part) and we need to follow the IEEE paper's data set up for this one. There are 60 patterns in which the users are playing this game. -Train, validate and test data using cross validation. | InProgress
Transfer all algorithms to Spark and all data to hadoop(hive) database | Yet to start
Connect Spark with Tableau (hive db) | To decide
Provide insights and a story board in Tableau | InProgress
Focus should be on finding out -will the players continue to play wow if they are into a particular guild, class, Level, Race -which are the class/race within wow game that attracts more players - can we recommend guilds to players so that they would not churn | Yet to start
Create final report and submit by Feb 16th | Yet to start